## Project Budget
Budget: SPM (Sustainable project Management)
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 3731600 | 0 | 3731600
MILESTONES & TASKS | LABOR |  | MATERIALS |  |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
| EMPLOYEE | WEEKS | RATE | UNITS | $/UNIT(S)
Task1:CUERRENT SYSTEM ASSESSMENT | 2 Engineers | 2 | 10000 | 2 | 100000 |  | 220000 |  | -220000
Task2: PURCHASE EQUIPMENT | 1 Manager | 8 | 20000 | 2 | 800000 |  | 1760000 |  | -1760000
Task3: HVAC INSTALLATION | 3 Technicians | 4 | 7000 | 2 | 100000 |  | 228000 |  | -228000
[6 empty] | Total | 2208000 | 0
Task1: SURVEY THE TEAMS REPLACEMENT | 1 Workers | 2 | 5000
Task2: FURNISH SECOND FLOOR | 2 Workers | 8 | 5000 | 100 | 12000 | 20000 | 1260000 |  | -1260000
Task3: VACUATE THE BASEMENT | 3 Workers | 2 | 5000 |  |  |  | 10000 |  | -10000
[6 empty] | Total | 1270000 | 0
Task1: TRAINING CONTENT PREPARATION | 3 HR Specialist | 2 | 10000 | 100 | 200 |  | 40000 |  | -40000
Task2: TRAINING | 3 Trainiers | 7 | 10000 |  |  |  | 70000 |  | -70000
[6 empty] | Total | 110000 | 0
Task1: HVAC POWER MEASUREMENT | 3 Engineers | 3 | 20000 |  |  |  | 60000 |  | -60000
Task2: PUE MEASUREMENT | 2 Engineers | 4 | 20000 |  |  |  | 80000 |  | -80000
[6 empty] | Total | 140000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 3731600 | 0