## Slide 1
Tasks |  | DEPENDENCY | Duration
1.1Current system assessment | A | - | 2 W
1.2 Purchase equipment | B | A | 8W
1.3 HVAC installation | C | B | 4W
2.1Survey the teams replacement | D | - | 2 W
2.2 Furniture second floor | E | D | 8W
2.3 Evacuate basement-Relocate the teams | F | E | 2W
3.1 Training content preparation | G | - | 2 W
3.2Training | H | G | 7W
4.1 HVAC power measurement | I | C | 3W
4.2 PUE Measurement | J | I | 4W
Precedence Diagram Method

## Slide 2
F
3
D
2
E
7
G
2
H
7
END
START
C
4
B
8
A
2
CP=ABCIJ=21W
2P=DEF=12W
3P=9W
I
3
J
4
PDM

## Slide 3
ES | 2 | EF
0 | 2
D
9 | 9 | 11
LS | F | LF
ES | 8 | EF
2 | 10
E
11 | 9 | 19
LS | F | LF
ES | 4 | EF
10 | 14
C
10 | 0 | 14
LS |  |  | LF
FS | 8 | EF
2 | 10
B
2 | 0 | 10
LS |  |  | LF
ES | 2 | EF
0 | 2
A
0 | 0 | 2
LS |  |  | LF
ES | 2 | EF
10 | 12
F
19 | 9 | 21
LS |  |  | LF
ES | 3 | EF
14 | 17
I
14 | 0 | 17
LS | F | LF
END
ES | 7 | EF
2 | 9
H
14 | 12 | 21
LS | F | LF
END
START
ES | 4 | EF
17 | 21
J
17 | 0 | 21
LS | F | LF
ES | 2 | EF
0 | 2
G
12 | 12 | 14
LS | F | LF