## Template - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
| Role A | Role B | Role C | Role D | Role E | Role F | Role G | Role H | Role I | Role J | Role K | Role L | Role M | Role N | Role O | Role P | Role Q
| CEO | International VP | Senior Projects Director | Technical Director | Development Director | Infrastructure Senior Manger | Financial Director | HR Director | Facilities Director | International Partners & investors | Employees | International Customers | HR Development Department | HAVAC Power Department | CLS Operation Department | Facility Operation Department | International relationship Manager
Deliverable
Two new sustainable systems of the (HVAC) in the cable landing stations (Abt,eldars) | I | I | C | A | I | C | C | I | I | I | I | I | I | R | I | I | I
Two PUE metric reports for (Abt,eldars) by the end of Project. (The power usage effectiveness)): Total amount of Energy used / IT equipment energy usage) | I | C | A | I | C | C | I | I | I | I | I | I | I | I | R | I | I
Upgrade & transfer fifteen offices from basement floor to be with good ventilation, lighting and furniture | I | C | I | I | I | C | C | A | I | I | I | I | I | I | I | R | I
Leadership Training program for supervisory positions to finish development workshops. | I | I | I | I | I | C | C | I | I | I | A | I | R | I | I | I | I