## Slide 1
SPM
1.REPLACEMENT HVAC
1.1CUERRENT SYSTEM ASSESSMENT
1.2 Purchase equipment
1.3 HVAC installation
2.REPLACEMENT OF OFFICES
2.1SURVEY THE TEAMS REPLACEMENT
2.2 FURNITURE SECOND FLOOR
2.3 VACUATE THE BASEMENT
3.DEVELOPMENT AND TRAINING FOR SUPERVISORY POSITIONS
3.1TRAINING CONTENT PREPARATION
3.2TRAINING
4.Utilization of PUE Matrices
4.1Equipment Power management
4.2 PUE Measurement
work breakdown structure(WBS)

## Slide 2
Milestones | CODE | Tasks | Owner | Duration
1.REPLACEMENT HVAC | 1.1 | 1.1 CURRENT SYSTEM ASSESSMENT | HVAC power department | 2 W
1.2 | 1.2 Purchase equipment | HVAC power department | 8W
1.3 | 1.3 HVAC installation | HVAC power department | 4W
2.REPLACEMENT OF OFFICES TO BETTER CONDITIONS | 2.1 | 2.1 SURVEY THE TEAMS REPLACEMENT | Facility department | 2 W
2.2 | 2.2 FURNITURE SECOND FLOOR | Facility department | 8W
2.3 | 2.3 VACUATE THE BASEMENT | Facility department | 3W
3.DEVELOPMENT AND TRAINING FOR SUPERVISORY POSITIONS | 3.1 | 3.1 TRAINING CONTENT PREPARATION | HR department | 2 W
3.2 | 3.2 TRAINING | HR development department | 7W
4.Utilization to PUE Matrices | 4.1 | 4.1 Equipment Power management | CLS department | 3W
4.2 | 4.2 PUE Measurement | CLS department | 4W
work breakdown structure(WBS)